## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2208-swen-261-01-a team4
Testing Team Name

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | whd 6/22 | Pass | nmr 7/14 | Pass | nmr 7/26
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | nmr 6/22 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | nmr 6/22 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | nmr 6/22 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | nmr 6/22 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | nmr 6/22 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | nmr 6/24 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | nmr 6/24 | Pass | yaa 7/14 | Pass | jrl 7/26
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | nmr 6/22 | Pass | yaa 7/14 | Pass | jrl 7/26
As a player, I want to make a simple move so that I can enact my strategy towards winning the game. | Given that I make a single move when I select submit a turn then I want the change to be reflected on the board. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
| Given that I make a single move when I select submit a turn then I want it to become my opponent’s turn. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
| Given that I make a single move when a jump move is possible then I want the move to be rejected. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
As a player I want to king a piece so that I can have a more useful piece to win the game. | Given that I move one of my pieces into the opponent's row, when I enter the space, then my piece will appear stacked and become a king. |  |  | Pass | whd 7/14 | Pass | jrl 7/26
| Given that my piece is a king, when I want to make a move, then I can move the piece in any direction as long as the space is valid. |  |  | Pass | whd 7/14 | Pass | jrl 7/26
| Given that it is my turn, when my piece is kinged, then my turn is ended. |  |  | Pass | whd 7/14 | Pass | jrl 7/26
As a player I want to be able to see buttons so that I can control the flow of the game. | Given that I have moved a piece and want it to go back to where it was when I select backup then the board must revert to what it was before. |  |  | Pass | nmr 7/14 | Pass | whd 7/26
| Given that I have selected and performed a move, when I click submit turn, then the board will update with my move for both players. |  |  | Pass | nmr 7/14 | Pass | whd 7/26
| Given that I have completed the game, when I am done, then I want an exit button to appear. |  |  | Pass | nmr 7/14 | Pass | whd 7/26
| Given that I have completed the game, when I press the exit button, then I want to return to the home screen. |  |  | Pass | nmr 7/14 | Pass | whd 7/26
| Given that I want to give up on the game, when I press the resign button, then I want the game to end with my opponent being declared the winner. |  |  | Pass | nmr 7/14 | Pass | whd 7/26
| Given I am playing, when it is someone's turn then I want the current player display to show the current player. |  |  | Pass | nmr 7/14 | Pass | whd 7/26
As a player I want to know if the game is over so that I can claim my victory or loss. | Given that my opponent has no pieces, when it becomes their turn to move, then I should win the game. |  |  |  |  | Pass | whd 7/26
| Given that my opponent cannot make a valid move, when it becomes their turn to move, then I should win the game. |  |  |  |  | Pass | whd 7/26
| Given that it is my opponent's turn, when my opponent resigns, then I should win the game. |  |  |  |  | Pass | whd 7/26
As a player I want to jump an opponents piece so that I can win the game. | Given that I make a jump move, when another jump move is possible (multiple), then I have to make that move. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
| Given that there are several different jump moves available, when I make my move, then I can choose which jump move to perform. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
| Given that there are possible jump moves, when I try to perform a simple move, then those moves are invalid. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
| Given that I make a jump move when I select submit a turn then I want the change to be reflected on the board. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
| Given that I make an incorrect jump move when I select submit a turn then I want the move to be rejected. |  |  | Pass | jrl 7/14 | Pass | jrl 7/26
As a player I want to be able to replay previous games so that I can review and learn them. | Given that I want to select a game to replay, when I go to the home page then I should see a list of games to replay. |  |  |  |  | Pass | nmr 7/26
| Given that I select a game to replay, when I click on it, then I should be able to see the starting board of the game. |  |  |  |  | Pass | nmr 7/26
| Given that I am replaying a game, when I want to view the next turn, then the board should update with the next turn. |  |  |  |  | Pass | nmr 7/26
| Given that I am replaying a game, when I want to view the previous turn, then the board should update with the previous turn. |  |  |  |  | Pass | nmr 7/26
| Given that I am done replaying a game, when I want to leave the replay mode, then I should see an exit button. |  |  |  |  | Pass | nmr 7/26
| Given that I am done replaying a game, when I click the exit button, then I should return to the home page. |  |  |  |  | Pass | nmr 7/26
As a player I want to be able to perform multiple jump moves so that I can capture more pieces. | Given that I jump over a piece when another jump is possible then I want to be able to jump again. |  |  |  |  | Pass | JRL 7/25
| Given that I submit a jump when another is still possible then I don't want the turn to end. |  |  |  |  | Pass | JRL 7/25
| Given that I submit a jump when another is still possible then I want to beagle to take said further jump. |  |  |  |  | Pass | JRL 7/25
| Given that I submit a jump when another is still possible then I want to be able to back up to my previous position. |  |  |  |  | Pass | JRL 7/25
| Given that I jump a piece then I want to be stopped from jumping over said piece again. |  |  |  |  | Pass | JRL 7/25
| Given that I am past the first jump then I want to only be able to place the piece in valid possible end spots. |  |  |  |  | Pass | JRL 7/25
| Given that I am performing multiple jumps before submitting my turn, when I land on the kinging row, then I want to not be able to make any further jumps. |  |  |  |  | Pass | JRL 7/25